## Sheet1
Live-Tech System
Sr | Task Id | Task Title | Project Name | Version | Task Duration | Created By | Assign To | Status | Status | Worked Time | Created At | overdue | assginto | Task Priority
| 1246 | Develop How to work page | LiveTechCMS.com | v0.1 | 05:00 | Muhammad Kashif | Abdul Rehman | Pending | Pending | 02:15:00 | 08/26/2021 | overdue | 34 | Normal
| 1240 | Ticket manager testing | Live-Tech System | v3.0 | 03:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 08:39:02 | 08/25/2021 | overdue | 34 | High
| 1229 | Checkout Page changes | Larsens Bakery | v3.0 | 03:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 02:14:27 | 08/16/2021 | overdue | 34 | Normal
| 1223 | RFQ Testing | Live-Tech System | v3.0 | 02:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 09:32:12 | 08/13/2021 | overdue | 34 | Normal
| 1222 | Asset manager testing | Live-Tech System | v3.0 | 02:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 02:10:08 | 08/13/2021 | overdue | 34 | Normal
| 1214 | Delete and create Customer & orders | Larsens Bakery | v3.0 | 03:00 | Muhammad Kashif | Abdul Rehman | Pending | Pending | 08:30:25 | 08/11/2021 | overdue | 34 | Normal
| 1209 | Testing ticket manager | Live-Tech System | 3 | 04:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 09:10:24 | 08/11/2021 | overdue | 34 | Normal
| 1202 | Working on ticket (QGV-301-3176) | mylive-tech.com | v0.1 | 08:00 | Muhammad Kashif | Abdul Rehman | Pending | Pending | 02:10:26 | 08/09/2021 | overdue | 34 | Normal
| 1193 | Change products price (TPlink) | Livetechstore.com | v0.1 | 08:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 05:20:10 | 08/06/2021 | overdue | 34 | Normal
| 1183 | change tplink prices and schedule | Live-Tech System | v3.0 | 08:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 08:00:00 | 08/05/2021 | overdue | 34 | Normal
| 1174 | Add remaining products | Live-Tech System | v3.0 | 05:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 07:58:50 | 08/03/2021 | overdue | 34 | Normal
| 1166 | Add products | Livetechstore.com | v0.1 | 03:00 | Muhammad Kashif | Abdul Rehman | Completed | Completed | 14:57:21 | 08/02/2021 | overdue | 34 | Normal